Assignment Sheet         

Citizens – Strategic Plan Goal #2

	Tasks
	Committee Members
	Notes

	Discovery:
To position Citizens for continued success and greater growth, the committee will develop a report by September 2017 sharing data needed to make an assessment of Citizens’ brand and its role within AHRC’s brand family.
	Mary McNamara;
Full Committee
	

	By Aug. 1, identify all programs, services and locations.
	Carolyn Ciatto;
Mary McNamara
	

	By Aug. 1, identify changing demographics of program participants (e.g., age, diagnoses, behaviors, Personal Outcome Measures).
	Chris O’Connor; 
Carolyn Ciatto,

	

	By Aug. 1, review primary sibling contact info to identify gaps in Central Enrollment/ MediSked.
	Joe Golio;
Zania Ledwidge
	

	By Aug. 1, gather all internal and external communications, distributions, policies and materials, including event fliers, website, brochures, business cards and content shared across social media.
	Carolyn Ciatto;

Mary McNamara;

Nicole Zerillo



	

	By Aug. 4, share org chart and staffing data (e.g., number of employees in specific roles; length of service; open positions; employee surveys).
	Chris O’Connor, sharing findings from Goal 5
	

	By Aug. 4, report on additional support positions created for Citizens’ changing audiences.
	Chris O’Connor, sharing findings from Goal 5
	

	By Aug. 4, share information and data from incident management procedures to identify risk trends for crisis communications.

	Nicole Zerillo, sharing findings from Goal 5
	

	By Aug. 7, share information and data on enrollment procedures, customer acquisition, engagement and services through Central Enrollment.
	Joe Golio; 
Zania Ledwidge

	

	By Aug. 7, create vendor list for the past three years.
	Joe Golio, sharing from Goal 5
	

	By Aug. 7, create a donor list for the past three years.
	Mary McNamara
	

	By Aug. 7, create a list of people and organizations that have volunteered over the past three years, as well as their areas of interest.
	Nicole Zerillo, sharing from Goal 5
	

	By Sept. 19, identify competitors and benchmark their services and communications vehicles (e.g., website, email, social media) beside Citizens’ assets.
	Full Committee
	

	By Sept. 19, evaluate status of current assessments, e.g., surveys, focus groups, etc.
	Carolyn Ciatto
	

	By TBD, identify legislative agenda, along with governmental and policy issues impacting the organization. 
	Roz Goldmacher;
George Bauer;
Mary McNamara;
Nicole Zerillo
	

	Strategy Development 
(Draft; Finalized According to Data Found in Discovery Phase):
By end of April 2018, assess findings as a committee, brainstorm in specialty areas in response to:
	Assignments TBD 
	

	Leadership, linkages and affiliation needed to strengthen current services and support future growth opportunities.

	
	

	-Evaluate opportunities to strengthen strategic alliances with partners, donors, and volunteers.
	
	

	-Evaluate areas of opportunities for fundraising and grants.
	
	

	-Leverage wealth prospecting software to increase funding.
	
	

	Examine existing marketing/ communications resources with current services and support future growth opportunities.
	
	

	-Clarify brand promise, attributes, key messages and drivers to respond to the findings and ideas generated by the committee. 
	
	

	-Develop content marketing calendar to update on ongoing basis to align with findings and opportunities.
	

	

	-Refine placement in brand architecture.
	

	

	-Create brand standards to ensure consistency across brand vehicles.
	
	

	Implementation (Draft; Finalized According to Strategy Phase):
Through August 2018, continue sustainable development of recommended growth opportunities for:
	Assignments TBD
	

	Implement brand identity guidelines including organizational access to materials bank.
	

	

	Roll out updated branding.
	

	

	Begin implementation of integrated content marketing plan for building brand awareness of specific programs among key audiences.
	
	

	Identify and connect with team members across organization through brand ambassador program to respond to timely topics and create features.
	
	

	Develop guidelines for staff to share their contributions to the organization’s mission, through newsletters, editorial schedule for blog and advocacy opportunities.
	
	

	Begin implementation of monitoring and measurement of marketing communications initiatives.
	
	


4

