Quarterly Update Report         

Citizens– Strategic Plan 2017—2020

Month:  JANUARY     Year:  2018

	Goal #2:  To define our brand and inter-relationship with AHRC and its affiliates.

	Chair: Mary McNamara

Committee: Roz Goldmacher, Carolyn Ciatto, Chris O’Connor, Joe Golio, Zania Ledwidge, Maryann Dellova, George Bauer, Nicole Zerillo



	Tasks
	Responsible
	Start
	Resources Required
	Outcomes/Measures
	Comments/Improvements

	Discovery

2.1  Develop a report, by end of September 2017, sharing data needed to make an assessment of Citizens’ brand and clarify its role within AHRC’s brand family
	Mary McNamara;

Full Committee, as assigned
	4/17


	Time of the Committee
	· Present findings in a report to Strategic Planning leadership. Complete.

	· Additional report submitted to highlight Citizens’ existing programs and services, as well as help define organization’s competitive advantage

	Development of

Brand Strategy

2.2  Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand
Development of

Brand Strategy

2.2  Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand
Development of

Brand Strategy

2.2  Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand
Development of

Brand Strategy

2.2  Develop a brand strategy, by end of April 2018, with recommendations for sustainable development of the brand

	Mary McNamara;

Full Committee, as assigned
	12/17
	Time of the Committee
	· Evaluate data from Discovery Phase (2.1) on Citizens’ brand assets and placement within the AHRC brand family. See submitted reports. 
· Present report of proposed strategy, tactical roll-out plan and budget to Strategic Planning leadership

	· Items to be assessed during strategy phase:

· Unique corporate identity, brand story and shared language 

· Internal campaign to onboard corporate identity and interrelationship with family of organizations
· Centralized communications, including review process, content collection, development and distribution to ensure materials are on brand and efforts not duplicated
· Roles and responsibility document to describe Community Resources’ services (e.g., development of forms, collateral, copy)

· Policies and procedures for group communications:
· Message development and distribution process

· Timeline

· Stakeholders
· Viability and/or role of PPC network in this updated system 
· Greater alignment needed for Camp Loyaltown as a program of Citizens through visual cues, messaging and social media
· Direction needed on which programs to highlight and promote as part of a family of organizations (e.g., self-direction featured prominently on site, yet only has one current registrant)
· The challenge of capturing self-direction personal outcome measure stories to incorporate into promotion and brand identity
· Strategy meetings called with:

· Citizens Management Team

· Website and recruitment updates

· CQL video to showcase person-centered excellence and brand interrelationship 

· Family Support Services:

· Programming needed for independent Family Education and Sibling Support, which can be repurposed into ongoing communications

· Sibling contacts should be moved to database
· Identified advocacy issues specific to groups can help bridge messaging gaps among family of organizations
· Ongoing strategy meetings held with:
· HR to develop communications for recruitment campaigns

· ComeUnity Recreation for updated materials and communications aligning with Citizens branding

· Central Enrollment to create more accessible “doorway” to services on website
· Camp Loyaltown team to discuss year-round support, ranging from recruitment for staff to ongoing respite programs

· Programs and Services to communicate MSC change-over in 2018

· Community Living Services to plan the second phase of #DSPsRock recognition  campaign

· Community Resources Events team to work on 2018 events
· Review AHRC Walk materials to better position Citizens in 2018
· Community Resources Volunteer Coordinator to better position Citizens’ volunteering opportunities


	Implementation

2.3  Implementation of plan, by end of August 2018, create and roll out updated brand utilizing storytelling components to resonate with stakeholders
Implementation

2.3  Implementation of plan, by end of August 2018, create and roll out updated brand utilizing storytelling components to resonate with stakeholders

	Mary McNamara;

Full Committee, as assigned
	4/18
	Time of the Committee
	· Update submitted branding with Strategic Planning leadership recommendations
· Create brand identity guidelines including organizational access to materials bank
· Leverage wealth prospecting software to increase fundraising

· Roll out updated branding
· Begin implementation of integrated content marketing plan for building brand awareness of specific programs among key audiences

· Mobilize brand ambassadors to respond to timely topics to create features

· Develop and distribute guidelines for staff to share their contributions to the organization’s mission through newsletters, editorial schedule, etc.

· Begin implementation of monitoring and measurement of marketing and communications initiatives





	· Community Resources in process of finalizing email template
· Ongoing promotion for Camp Loyaltown, including the fundraising events, Glam Slam and Bowlathon

· New signage, brochures and event logos developed for events

· Glam Slam event featured in Newsday, FiOS1 Long Island and “The Chapters Rap with Steve Vaccaro” podcast

· CQL video in production to showcase person-centered excellence and brand interrelationship through testimonials 
· Development of ComeUnity Starz logo incorporating Citizens and ComeUnity Recreation branding; redesign of brochure with new branding and layout
· Advertising placement in SUNY Old Westbury Athletics calendar for ComeUnity Sports volunteer opportunities

· Advertising placement secured on Long Island Special Child website directory for Camp Loyaltown 
· Advocacy issues, including Medicaid and #bfair2directcare, cross-promoted as part of AHRC family of organizations

· Working toward standardized business closure communications

· Volunteer Online portal is operational with more accessible training schedule
· MSC transition campaign underway


	2.4  On a quarterly basis, report on progress of newly developed brand assets
	Mary McNamara;

Full Committee, as assigned
	4/18
	Time of the Committee
	· Measurement report to inform, refine or expand existing recommendations
	





3

