| Tasks | Committee Members | Notes |
| --- | --- | --- |
| Discovery: To position Citizens for continued success and greater growth, the committee will develop a report by September 2017 sharing data needed to make an assessment of Citizens’ brand and its role within AHRC’s brand family. | Mary McNamara; Full Committee |  |
| By Aug. 1, identify all programs and services. | Carolyn Ciatto; Mary McNamara |  |
| By Aug. 1, identify changing demographics of program participants (e.g., age, diagnoses, behaviors, Personal Outcome Measures). | Chris O’Connor; Carolyn Ciatto, |  |
| By Aug. 1, review primary sibling contact info to identify gaps in Central Enrollment/ MediSked. | Joe Golio; Zania Ledwidge |  |
| By Aug. 1, gather all internal and external communications materials, including event fliers, website, brochures, business cards and content shared across social media. | Carolyn Ciatto; Mary McNamara; Nicole Zerillo |  |
| By Aug. 4, share information and staffing data (e.g., number of employees in specific roles; length of service; open positions; employee surveys). | Chris O’Connor, sharing findings from Goal 5 |  |
| By Aug. 4, report on additional support positions created for Citizens’ changing audiences. | Chris O’Connor, sharing findings from Goal 5 |  |
| By Aug. 4, share information and data from incident management procedures to identify risk trends for crisis communications. | Nicole Zerillo, sharing findings from Goal 5 |  |
| By Aug. 7, share information and data on enrollment procedures, customer acquisition, engagement and services through Central Enrollment. | Joe Golio: Zania Ledwidge |  |
| By Aug. 7, create vendor list for the past three years. | Joe Golio |  |
| By Aug. 7, create a donor list for the past three years. | Mary McNamara |  |
| By Aug. 7, create a list of people and organizations that have volunteered over the past three years, as well as their areas of interest. | Nicole Zerillo |  |
| By Sept. 19, identify competitors and benchmark their services and communications vehicles (e.g., website, email, social media) beside Citizens’ assets. | Full Committee |  |
| By TBD, identify legislative agenda, along with governmental and policy issues impacting the organization. | Roz Goldmacher; George Bauer; Mary McNamara; Nicole Zerillo |  |
| Strategy Development (Draft; Finalized According to Data Found in Discovery Phase): By end of April 2018, assess findings as a committee, brainstorm in specialty areas in response to: | Assignments TBD |  |
| Leadership, linkages and affiliation needed to strengthen current services and support future growth opportunities. |  |  |
| -Evaluate opportunities to strengthen strategic alliances with partners, donors, and volunteers. |  |  |
| -Evaluate areas of opportunities for fundraising and grants. |  |  |
| -Leverage wealth prospecting software to increase funding. |  |  |
| Examine existing marketing/ communications resources with current services and support future growth opportunities. |  |  |
| -Clarify brand promise, attributes, key messages and drivers to respond to the findings and ideas generated by the committee. |  |  |
| -Develop content marketing calendar to update on ongoing basis to align with findings and opportunities. |  |  |
| -Refine placement in brand architecture. |  |  |
| -Create brand standards to ensure consistency across brand vehicles. |  |  |
| Implementation (Draft; Finalized According to Strategy Phase): Through August 2018, continue sustainable development of recommended growth opportunities for: | Assignments TBD |  |
| Implement brand identity guidelines including organizational access to materials bank. |  |  |
| Roll out updated branding. |  |  |
| Begin implementation of integrated content marketing plan for building brand awareness of specific programs among key audiences. |  |  |
| Identify and connect with team members across organization through brand ambassador program to respond to timely topics and create features. |  |  |
| Develop guidelines for staff to share their contributions to the organization’s mission, through newsletters, editorial schedule for blog and advocacy opportunities. |  |  |
| Begin implementation of monitoring and measurement of marketing communications initiatives. |  |  |