| Tasks | Committee Members | Notes |
| --- | --- | --- |
| Discovery: To position Citizens for continued success and greater growth, the committee will develop a report by September 2017 sharing data on current operational capacity. | Joe Milone; Nicole Zerillo; Full Committee |  |
| By Aug. 1, identify all programs and services | Nicole Zerillo, sharing findings from Goal 2 |  |
| By Aug. 1, identify changing demographics of program participants (e.g., age, diagnoses, behaviors, Personal Outcome Measures). | Chris O’Connor, sharing findings from Goal 2 |  |
| By Aug. 1, review primary sibling contact info to identify gaps in Central Enrollment/ MediSked. | Joe Golio, sharing findings from Goal 2 |  |
| By Aug. 1, gather all internal and external communications materials, including event fliers, website, brochures, business cards and content shared across social media. | Nicole Zerillo, sharing findings from Goal 2 |  |
| By Aug. 4, share org chart and staffing data (e.g., number of employees in specific roles; length of service; open positions; employee surveys). | Chris O’Connor; Jason Persan |  |
| By Aug. 4, report on additional support positions created for Citizens’ changing audiences. | Chris O’Connor; Jason Persan |  |
| By Aug. 4, share information and data from incident management procedures. | Ann Miller | Shared documents; under review. |
| By Aug. 7, share information and data on enrollment procedures, customer acquisition, engagement and services through Central Enrollment. | Joe Golio, sharing findings from Goal 2 |  |
| By Aug. 7, create a vendor list for the past three years. | Joe Golio; Nicole Zerillo |  |
| By Aug. 7, create a list of people and organizations that have volunteered over the past three years, as well as their areas of interest. | Nicole Zerillo |  |
| By Aug. 7, create a donor list for the past three years. | Nicole Zerillo, sharing findings from Goal 2 |  |
| By Sept. 19, identify competitors and benchmark their services and brand communications vehicles (e.g., website, email, social media) beside Citizens’ assets. | Chris O’Connor, sharing findings from Goal 2 |  |
| By TBD, identify legislative agenda, along with governmental and policy issues impacting the organization. | Nicole Zerillo, sharing findings from Goal 2 |  |
| Strategy Development (Draft; Finalized According to Data Found in Discovery Phase): By end of April 2018, assess findings as a committee, brainstorm in specialty areas in response to: | Joe Milone; Nicole Zerillo |  |
| Staffing and training resources needed to strengthen current services and support future growth opportunities. | Nicole Uterano; Jason Persan |  |
| Quality assurance resources needed to strengthen current services and support future growth opportunities. | Ann Miller |  |
| Technological resources needed to strengthen current services and support future growth opportunities. | Tony Daniels; Joe Milone |  |
| Update firewall by Q1 2017 to increase accessibility to digital assets across organization. | Tony Daniels; Joe Milone | Complete |
| Connect VPN to all sites by Q4 2018 | Tony Daniels; Joe Milone |  |
| Update Wi-Fi by Q1 2018 to increase accessibility to digital assets across organization. | Tony Daniels; Joe Milone |  |
| Finalize installation of Avaya phone system, including on-site coverage off site through Outlook, phone and app with testing through Q3 2017 and Q3 2018 roll out. | Tony Daniels; Joe Milone |  |
| App in testing. | Tony Daniels; Joe Milone |  |
| Update Intranet for end of Q1 2018 to offer more accessible online venue to access necessary employee information. | Tony Daniels; Joe Milone |  |
| Leadership, linkages and affiliation needed to strengthen current services and support future growth opportunities. | Joe Golio; Nicole Zerillo |  |
| Evaluate opportunities to strengthen strategic alliances with partners, donors, and volunteers. | Nicole Zerillo |  |
| Evaluate areas of opportunities for fundraising and grants. | Nicole Zerillo |  |
| Leverage wealth prospecting software to increase funding. | Nicole Zerillo |  |
| Examine existing marketing/ communications resources with current services and support future growth opportunities. | Nicole Zerillo |  |
| Clarify brand promise, attributes, key messages and drivers to respond to the findings and ideas generated by the committee. | Nicole Zerillo |  |
| Develop content marketing calendar to update on ongoing basis to align with findings and opportunities. | Nicole Zerillo |  |
| Refine placement in brand architecture. | Nicole Zerillo |  |
| Create brand standards to ensure consistency across brand vehicles. | Nicole Zerillo |  |
| Implementation (Draft; Finalized According to Strategy Phase): Through August 2018, continue sustainable development of recommended growth opportunities for: | Joe Milone; Nicole Zerillo |  |
| Program pipeline. | Chris O’Connor; Nicole Uterano |  |
| New business. | Joe Golio |  |
| Quality benchmarks, such as medical policies and procedures anticipating growth. | Ann Miller |  |
| Fundraising and grants | Nicole Zerillo |  |
| Technology | Joe Milone |  |
| Brand awareness | Nicole Zerillo |  |
| Implement brand identity guidelines including organizational access to materials bank. | Nicole Zerillo |  |
| Roll out updated branding. | Nicole Zerillo |  |
| Begin implementation of integrated content marketing plan for building brand awareness of specific programs among key audiences. | Nicole Zerillo |  |
| Identify and connect with team members across organization through brand ambassador program to respond to timely topics and create features. | Nicole Zerillo |  |
| Develop guidelines for staff to share their contributions to the organization’s mission, through newsletters, editorial schedule for blog and advocacy opportunities. | Nicole Zerillo |  |
| Begin implementation of monitoring and measurement of marketing communications initiatives. | Nicole Zerillo |  |