| Goal #5: To build the infrastructure needed to meet organizational goals, e.g. operations, technology, communications, quality assurance, marketing and alliances |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Co-Chairs: Nicole Zerillo, Joe Milone Committee: Tony Daniels, Nicole Uterano, Joe Golio, Ann Miller, Chris O’Connor, Jason Persan |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| 5.1 Develop a report, by September 2017, evaluating current operational capacity | Joe Milone; Nicole Zerillo; Full Committee | 4/1/17 | Time of the Committee | - Share org chart and staffing data (e.g., number of employees in specific roles; length of service; open positions, etc.) (completed) - Report on additional support positions created for Citizens’ changing audiences (completed) - Share information and data from incident management procedures (completed) - Create a list of vendors, as well as corporate and individual volunteers from the past three years (completed) - Present findings in a report to Strategic Planning leadership | - Completed competitive landscape section (attached) of discovery report. Remainder will be shared by last week of October. - Issues hindering high-performance infrastructure: - Six databases and lists (i.e., MediSked, Raiser’s Edge, Purchase Connection, UltiPro, Bunk 1, Heidi’s Desk) are required to build full contact lists. - Multiple challenges related to obtaining and maintaining contact information. - Vendor list should be thought of as a potential solicitation list. Need name and contacts for decisionmakers. - Inconsistent branding and access to templated materials. - With planned residential growth, greater process coordination and set timelines needed to install network infrastructure in a timely fashion and build community relations. - Need comprehensive schedule for home openings with locations, timeframes and support needs for IT and Community Resources. - Increasing communications support needed – with year-round maintenance of internal and external communications channels for both Citizens and Camp Loyaltown, which have their own respective email, mailings, websites and social media channels. |
| 5.2 By end of April 2018, assess findings and propose recommendations to address current and forthcoming infrastructure needs | Joe Milone; Nicole Zerillo; Full Committee | 12/31/17 | Time of the Committee | - Evaluate data from Discovery Phase (5.1) - Compile updated report on recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years - Present report of proposed strategy, tactical plan and budget to Strategic Planning leadership | - Continue to recommend assignment sheet to connect all Virtual Private Networks (VPN) to all sites by Q4 2018. - Streamline contact collection process and distributions. - Consider evaluation of what programs we currently have and how to better manage. - IT/Operations/Community Resources to assess internal solutions available and whether external consultant needed. - Recommend centralized contact program as well as formal process for communications distributions to key audiences. - Build a functional email signature coded to anticipate healthcare organization fire walls. - Recommend service development of family education and sibling support groups by location. - Clarify how the Café, UltiPro and PPC programs are utilized and when appropriate. - Working toward standardized business closure information (e.g., snow day closings). - Recommend development of tech library of tools, such as iPad, iPhone or video camera, that team members can “check out” to capture storytelling components for programs. - Proposing new development meeting with Operations, IT and Community Resources to be able to plan for residential expansion. - For enhanced marketing, request leadership identify strategic growth areas and programs to emphasize, such as respite or self-direction. - As directed by Goal 1 and 2 Committees, will plan to integrate legislative agenda, along with governmental and policy issues impacting the organization into discovery report. - Propose increased resources to maintain and generate content for Citizens and Camp Loyaltown’s internal and external communications channels. |
| 5.3 Through August 2018, implement approved tactical plan while continuing to identify areas for sustainable development | Joe Milone; Nicole Zerillo; Full Committee | 4/1/18 | Time of the Committee; Budget | - Incorporate recommendations from Strategic Planning leadership - Implementation of approved strategy, tactical plan and benchmarks - Compile report with new recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years | - Firewall upgrade completed. - Install wireless infrastructure by end of year (currently 6 sites completed). - Mobile Device Management (MDM) to be installed on all corporate phones by end of the year and all corporate devices by end of 2018. - Company-wide phone list completed, with names, phone numbers, locations and job titles, according to cost center codes. PPCs to distribute. - Soft-launch of Volunteer Portal. - Updated photo releases and email captures for ComeUnity Sports and Camp Loyaltown’s Bunk 1. |
| 5.4 On a quarterly basis, compile measurement report sharing data on progress of newly developed infrastructure assets | Joe Milone; Nicole Zerillo; Full Committee | 4/1/18 | Time of the Committee | - Compile measurement report - Use measurement report to inform, refine or expand existing recommendations |  |