| Goal #5: To build the infrastructure needed to meet organizational goals, e.g. operations, technology, communications, quality assurance, marketing and alliances |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Co-Chairs: Nicole Zerillo, Joe Milone Committee: Tony Daniels, Nicole Uterano, Ann Miller, Chris O’Connor, Jason Persan, Kim Shouler |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| 5.1 Develop a report, by September 2017, evaluating current operational capacity | Joe Milone; Nicole Zerillo; Full Committee | 4/1/17 | Time of the Committee | - Present findings in a report to Strategic Planning leadership. Complete. | - Additional report submitted to highlight Citizens’ existing programs and services, as well as help define organization’s competitive advantage. Complete. |
| 5.2 By end of Q1 2019, assess findings and propose recommendations to address current and forthcoming infrastructure needs 5.2 By end of Q1 2019, assess findings and propose recommendations to address current and forthcoming infrastructure needs 5.2 By end of Q1 2019, assess findings and propose recommendations to address current and forthcoming infrastructure needs 5.2 By end of Q1 2019, assess findings and propose recommendations to address current and forthcoming infrastructure needs | Joe Milone; Nicole Zerillo; Full Committee Joe Milone; Nicole Zerillo; Full Committee Joe Milone; Nicole Zerillo; Full Committee | 12/31/17 12/31/17 12/31/17 | Time of the Committee Time of the Committee Time of the Committee | - Evaluate data from Discovery Phase (5.1). Complete. - Compile updated report on recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years - Present report of proposed strategy, tactical plan and budget to Strategic Planning leadership - Evaluate data from Discovery Phase (5.1). Complete. - Compile updated report on recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years Present report of proposed strategy, tactical plan and budget to Strategic Planning leadership - Evaluate data from Discovery Phase (5.1). Complete. - Compile updated report on recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years Present report of proposed strategy, tactical plan and budget to Strategic Planning leadership | - By end of May, present strategies for: - Clarification of Citizens vs. AHRC’s ownership of unique programs and resources - Make company space in Plainview more easy to navigate for staff and visitors with visual cues, such as color-coordinated hallways - Develop actionable organizational chart highlighting roles/responsibilities and points of contact - To be made available on new intranet, Connect - To keep digital chart up to date, plan how to maintain - Plan Citizens “welcome” toolkit to help inform new program participants and families on services and points of contact - Inconsistent branding and quality control: - Approved email signature and confidentiality/business disclosure footer - Progress made on email template for all staff in family of organizations; third draft in process - User-friendly portal and instructions to be developed - Ready-to-order and approved collateral through printer/Purchasing Department - Content sharing across departments who produce publications (i.e. Community Resources, HR and Compass) - Testing content-sharing programs, including Asana, Slack and the new intranet, Connect, to ensure simultaneous access to stories and tracking of how/when used - Tech upgrades for new and existing houses - Plan training in professional offices within houses to lessen IT support time - Building security - Meeting set with Jason Persan, security committee chair, to align security and infrastructure committee goals - Strategies to be proposed in Q4 2018 on: - Residential expansion issues - Development meeting with Operations, IT and Community Resources to be scheduled - Inconsistent routing of incoming calls and mail - Viability of where/when to incorporate automated phone systems - Training and needs of receptionists - Continued training of employees on Avaya phone system - Further workforce development/training to enhance efficiencies across the organization (e.g., how to use Excel, take a picture for newsletter/social media placement, Purchase Connection) - Kim Shouler joined infrastructure committee to provide Accounting perspective and feedback on issues, such as the updating of accounting codes to be more user friendly - Policies and procedures for: - Centralized communications, content collection process and timeline for scheduling distributions - Current business practices, such as out-of-office messaging, setting a meeting with a “shared calendar,” etc. - Use of different tools: UltiPro, Connect, etc. - Increasing communications support needed – with year-round maintenance of internal and external communications channels for both Citizens and Camp Loyaltown, which have their own respective email, print mailings, websites and social media channels - Goal set of doubling Facebook followers due to account’s success in summer staff recruitment - Strategies to be proposed in Q1 2019 on: - Disconnect among the organization’s disparate data systems (i.e., MediSked, Raiser’s Edge, Purchase Connection, UltiPro, Bunk 1, Heidi’s Desk) - E-filing and securing of sensitive e-documents through admin files with encryption - Service development of family education and sibling support groups solely for Citizens - Anticipated growth of people supported, staff and resulting investigations/challenges related to compliance/ reporting requirements |
| 5.3 Through Q2 2019, implement approved tactical plan while continuing to identify areas for sustainable development | Joe Milone; Nicole Zerillo; Full Committee | 4/1/18 | Time of the Committee; Budget | - Incorporate recommendations from Strategic Planning leadership - Implementation of approved strategy, tactical plan and benchmarks - Compile report with new recommendations for the sustainable development of new programs, staffing/training, quality assurance, technology, opportunities to contract out services, organizational partnerships/affiliations, staff partnerships/affiliations, fundraising and grants, as well as brand marketing communications – now and over the next three years | - Development of new intranet, Connect: - Updated to increase accessibility to internal communications materials - In process of migrating all departments to access internal communications material - IT and Community Resources connected on site rebrand - Email signature template for Citizens in development by Community Resources - Progress made on email template for all staff in family of organizations; third draft in process - Email confidentiality/disclosures in process - Participation in Emergency Responder March 9 meeting on aligning tech and communications tools for committee - Tech upgrades for new and existing houses - All houses upgraded to the new wireless standard - Any new house will have the new wireless technology - Expansion of online storage for media and communications materials to G:Drive: CRC Media, for maintenance of high-res files (7,117GB available) - Additional steps taken toward more cloud-based capabilities (TBD) - New devices and administrative enhancements for new housing - Currently testing new Chrome books - New Citrix farm installed and users are currently being migrated to it - Mobile Device Management (MDM) installed on all corporate phones |
| 5.4 On a quarterly basis, compile measurement report sharing data on progress of newly developed infrastructure assets | Joe Milone; Nicole Zerillo; Full Committee | 4/1/18 | Time of the Committee | - Compile measurement report - Use measurement report to inform, refine or expand existing recommendations |  |