| Goal #2: To define our brand and inter-relationship with AHRC and its affiliates. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Chair: Mary McNamara Committee: Roz Goldmacher, Carolyn Ciatto, Chris O’Connor, Zania Ledwidge, Maryann Dellova, Heidi Klewicki, Nicole Zerillo |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| 2.1 Create brand consistency and awareness on staff communications materials | Mary McNamara; Full Committee, as assigned | 4/17 | Time of the Committee | - Complete email signature/business disclosure footer, user-friendly upload portal and instructions - Complete business card update and finalize ready-to-order process with printer and purchasing department - Complete Style Guide for consistent writing, editing and proofing conventions - Complete Brand Guide for consistent logo use - Complete FAQ for all staff on development of marketing materials, emails and media processes - Complete digital organizational chart with headshot, title, email and extension with Central Enrollment - Complete “welcome” toolkit for new staff and families on available services and points of contact - Complete MSC transition communications campaign - Complete strengthening Camp Loyaltown’s presence on Citizens website - Complete co-branding Camp Loyaltown’s materials as a “program of Citizens Options Unlimited” - Propose id lanyards with logo/tag line | - Finalized design of email signature; shared with IT to begin testing, coding and uploading to Outlook - Brainstormed digital organizational chart with Central Enrollment, discussed with IT for intranet, and IT process of looping in HR to discuss viability of maintenance and execution - Final MSC transition campaign letters and emails scheduled, as provided - On an ongoing basis, official communications are packaged with Citizens brand wrappers for notices, emails, letters, etc. - Initiated design process for Camp Loyaltown logo, identifying as “a program of Citizens Options Unlimited” - Updated Citizens Camp Loyaltown Instagram account to tag/identify as a program of Citizens Options Unlimited |
| 2.2 On an ongoing basis, engage people we support, families, staff and friends on our mission statement, accreditation and opportunities to connect | Mary McNamara; Full Committee, as assigned | 4/17 | Time of the Committee | - Complete campaign highlighting CQL and Compass designations - Complete campaign recognizing #DSPsRock - Complete Staff Appreciation Day recognition - Continue volunteer engagement campaign - Complete mission poster - Complete recognition of Camp capital campaign contributors - Continue ongoing meetings with external fundraising committees | - Mission poster layout is complete with request for residential image and photo consents in process - A campaign with prizes and incentives is in development for Q1 2018 to engage on mission - A 2018 #DSPsRock campaign in development for summer 2018; schedule meeting for Citizens and AHRC CLS teams and Community Resources - Scheduled to post Staff Appreciation Day images across website, social media and recruitment materials - Volunteer communications are sent on a monthly basis to connect on upcoming opportunities - Monthly meetings with external fundraising committees for Camp held for Casino Loyale and Paint and Sip events - Received approval to accept donations on Facebook page |
| 2.3 By Q4 2018, develop promotional materials to increase awareness of Citizens’ community, success stories, services and professional opportunities in Nassau and Suffolk Counties | Mary McNamara; Full Committee, as assigned | 12/17 | Time of the Committee | - Complete brochure overview of all Citizens services (Central Enrollment), as well as part of family of organizations - Completed updates for 2018 Camp brochure, posters, testimonial cards and Plexiglass inserts - Update ComeUnity brochure for 2018-19 season along with registration process - Complete digital recruitment ads (monthly) - Reach nearly double social media followers on Camp Loyaltown social media channels | - Community Resources trained new Camp staff on social media as well as developed a packet on policies and best practices |
| 2.4 On an ongoing basis, ensure that the people we support and our staff are well represented on our website, social media, media pitches and internal communications pieces | Mary McNamara; Full Committee, as assigned | 12/17 | Time of the Committee | - Track the continued representation of the people we support, staff, families, friends and partners throughout our communications channels - Complete streamlining of content-gathering process with new collection tool, Policies & Procedures document for all departments who produce publications and/or group communications - Complete Casino Loyale event - Completed Paint and Sip event - Completed Bake Sale - Completed JP Morgan Splash Bash Event in NYC - Completed ongoing advertising placements in Long Island Business News’ Book of Lists, SUNY Old Westbury Athletics Calendar (ComeUnity and Long Island Special Child (Camp Loyaltown) | - Currently testing content-sharing tools (e.g., Asana, Slack, Connect) for departments producing publications - Tested out WuFoo for ticket system of marketing requests, similar to IT’s help desk - Request communications contact to keep Community Resources updated on agency openings, success stories, etc. - Discussed updates of advocacy platform and outreach in Government Relations Committee - Connected with HR to continue implementation of monthly online advertising campaign - Casino Loyale ad finalized; shared in save-the-date email sent as well as Rose Ball Journal ad - Wrapped JP Morgan Splash Bash and now in process of promoting in JP Morgan newsletter and receiving approval for inclusion on Citizens website and social media channels - Finalizing schedule for JP Morgan team to visit Camp |