| Goal #5: To build the infrastructure needed to meet organizational goals, e.g. operations, technology, communications, quality assurance and alliances |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Co-Chairs: Nicole Zerillo, Joe Milone Committee: Tony Daniels, Nicole Uterano, Ann Miller, Chris O’Connor, Jason Persan, Kim Shouler, Nicci Kern |  |  |  |  |  |
| Tasks | Responsible | Start | Resources Required | Outcomes/Measures | Comments/Improvements |
| 5.1 On an ongoing basis, update office space for more cohesive operations, professional presentation of services and increased delineation from AHRC | Joe Milone; Nicole Zerillo; Full Committee | 6/22/18 | Time of the Committee; Budget | - Propose further demarcation of Citizens’ space in Plainview office with one section set for full team, unique entry way marked by outdoor signage, and conference rooms - Propose telephone lines updated to route to Citizens-specific line with automated attendant and/routing to Citizens receptionist - Propose naming conference rooms to align with brand and increase visibility - Completed painting hallways for better navigation of services | - These proposed outcomes might best coincide with building security updates - District Council 9 of the International Union of Painters and Allied trades color coded the hallways for different programs in late April |
| 5.2 On an ongoing basis, integrate tech upgrades that will ensure the continued sustainability and growth of Citizens programs | Joe Milone; Nicole Zerillo; Full Committee | 4/1/17 | Time of the Committee | - Resolve disconnect among the organization’s disparate data systems (i.e., MediSked, Raiser’s Edge, Purchase Connection, UltiPro, Bunk 1, Heidi’s Desk) - Complete tech upgrades, including new wireless technology, for new and existing houses - Complete upgrade for e-filing and securing of sensitive e-documents through admin documents with encryption - Complete testing phase for new devices and administrative enhancements for new housing - Complete development of intranet to serve as a tool to schedule trainings, offer a digital organizational chart of contacts, and increase engagement on agency policies | - IT in process of rolling out new Chrome books and moving employees to the new Citrix farm - Community Resources in process of testing content-sharing programs, including Asana, Slack, WuFoo and the new intranet, Connect, to ensure simultaneous access to stories, images and tracking of how/when used for all departments producing publications (e.g., HR, Compass, Community Resources) - IT in process of migrating all departments to access internal communications material |
| 5.3 By Q4 2018, create brand consistency and awareness through communications initiatives | Joe Milone; Nicole Zerillo; Full Committee | 4/1/17 | Time of the Committee | - Complete email signature/business disclosure footer, user-friendly upload portal and instructions - Complete business card update and finalize ready-to-order process with printer and purchasing department - Complete Style Guide for consistent writing, editing and proofing conventions - Complete Brand Guide for consistent logo use - Complete FAQ for all staff on development of marketing materials, emails and media process - Complete digital organizational chart with headshot, title, email and extension with Central Enrollment - Complete Policies & Procedure - Complete promotional plan and alliance-building in areas where new homes opening | - Community Resources finalized design of email signature template, shared with IT to begin testing, coding and generate instructions on how users can change their email signature - Brainstormed digital organizational chart with Central Enrollment, discussed with IT for AHRC Connect, and in process of looping in HR to discuss viability of maintenance/execution - Added Nicci Kern to goal committee to align new houses with resources needed to build partnerships and community awareness in Suffolk - Currently researching capacity issue regarding increased communications for Citizens and Camp Loyaltown |
| 5.5 By Q3 2019, ensure staff supported to meet demands of changing workplace through updated training and engagement | Joe Milone; Nicole Zerillo; Full Committee | 4/1/17 | Time of the Committee | - Complete “welcome” toolkit to help inform new program participants and families on services and points of contact - Complete accounting code update and FAQ to clarify process on items not included - Complete FAQ document on current databases and their respective purposes - Complete Policies & Procedures for: - Centralized communications, content collection process and timeline for scheduling distributions - Current business practices, such as out-of-office messaging, setting a meeting with a “shared calendar,” etc. - Complete updated tech trainings for staff to close gaps on necessary programs, such as Excel and Outlook | - Further workforce development/training to enhance efficiencies across the organization (e.g., how to use Excel, take a picture for newsletter/social media placement, Purchase Connection) - Connecting with local Microsoft and Roslyn Savings Bank contacts to volunteer ; offer staff trainings respectively on Outlook, Excel and Word as well as financial planning - Through internal processes, resolved quality assurance question raised in previous strategy sessions regarding the anticipated growth of people supported, investigations/challenges related to compliance and reporting requirements |